## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Naha Mondal | 2026-10-14 | Python syntax validation did not work as expected. | Sprint 1 | Naha Mondal | Logical | Corrected the validation logic and retested invalid Python input. | 2026-10-10 | Closed | Verified after retesting.
2 | Naha Mondal | 2026-10-14 | Analysis findings did not appear in the results panel. | Sprint 1 | Naha Mondal | User Interface | Corrected the results rendering issue and retested the analysis workflow. | 2026-10-11 | Closed | Retest the analysis workflow.
3 | Naha Mondal | 2026-10-14 | Duplicated validation logic made code maintenance difficult. | Sprint 1 | Naha Mondal | Maintainability | Refactored the duplicated logic and checked existing functionality. | 2026-10-12 | Closed | Refactoring verified.
4 | Naha Mondal | 2026-10-14 | Security findings did not follow the defined reporting conventions. | Sprint 1 | Naha Mondal | Standards | Updated the reporting logic and checked the affected findings | 2026-10-13 | Closed | Output verified against the defined conventions.
5 | Naha Mondal | 2026-10-29 | Cyclomatic complexity calculation in Code Analysis Agent incorrectly counted non-branching expressions. | Sprint 2 | Naha Mondal | Logical | Updated AST traversal logic in _calculate_cyclomatic_complexity to accurately count decision branch nodes. | 2026-10-25 | Closed | Verified with complex conditional benchmark test cases.
6 | Naha Mondal | 2026-10-29 | Hardcoded API credentials detected by Security Agent were exposed in plain text in finding evidence. | Sprint 2 | Naha Mondal | Security | Implemented secret masking to redact sensitive token values with asterisks prior to output generation. | 2026-10-26 | Closed | Verified credential redaction across Python and Java test samples.
7 | Naha Mondal | 2026-10-29 | Multi-Agent Orchestrator duplicate findings occurred when merging outputs from concurrent agent threads. | Sprint 2 | Naha Mondal | Logical | Enhanced _merge_findings with deduplication key hashing by rule ID, line number, and agent provenance. | 2026-10-27 | Closed | Verified parallel thread execution and unified findings deduplication.
8 | Naha Mondal | 2026-10-29 | Unified findings list was unsorted, causing low-severity style warnings to display above critical vulnerabilities. | Sprint 2 | Naha Mondal | User Interface | Added descending sort by numeric severity_score in orchestrator to prioritize critical security flaws. | 2026-10-28 | Closed | Verified sorted order with Critical (9.5+) findings prioritized at top.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others