## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Naha Mondal | 2026-10-14 | Python syntax validation did not work as expected. | Sprint 1 | Naha Mondal | Logical | Corrected the validation logic and retested invalid Python input. | 2026-10-10 | Closed | Verified after retesting.
2 | Naha Mondal | 2026-10-14 | Analysis findings did not appear in the results panel. | Sprint 1 | Naha Mondal | User Interface | Corrected the results rendering issue and retested the analysis workflow. | 2026-10-11 | Closed | Retest the analysis workflow.
3 | Naha Mondal | 2026-10-14 | Duplicated validation logic made code maintenance difficult. | Sprint 1 | Naha Mondal | Maintainability | Refactored the duplicated logic and checked existing functionality. | 2026-10-12 | Closed | Refactoring verified.
4 | Naha Mondal | 2026-10-14 | Security findings did not follow the defined reporting conventions. | Sprint 1 | Naha Mondal | Standards | Updated the reporting logic and checked the affected findings | 2026-10-13 | Closed | Output verified against the defined conventions.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others